## MVIS-VandeBharat
Module | Activity | Description | Owner | Priority | Status | Target Date | Plan File Path
Live Train Monitor | Requirement Finalization | Define train movement workflow and live data source integration | BA/Product Team | High | In Progress | 2026-06-20 | excel-plan/01-live-train-monitor/plan.md
Live Train Monitor | UI Wireframe | Design animated rake visualization | UI/UX | High | In Progress | 2026-06-20 | excel-plan/01-live-train-monitor/plan.md
Live Train Monitor | WebSocket Integration | Implement real-time data streaming | Backend | High | In Progress | 2026-06-20 | excel-plan/01-live-train-monitor/plan.md
Live Train Monitor | Train Status API | Develop API for train detection status | Backend | High | In Progress | 2026-06-20 | excel-plan/01-live-train-monitor/plan.md
Live Train Monitor | Frontend Dashboard | Build live train tracking screen | Frontend | High | In Progress | 2026-06-20 | excel-plan/01-live-train-monitor/plan.md
Live Train Monitor | Performance Testing | Verify real-time update latency | QA | High | In Progress | 2026-06-20 | excel-plan/01-live-train-monitor/plan.md
Defect Alert Console | Alert Workflow Definition | Define defect lifecycle and severity levels | BA | High | Done | 2026-06-20 | excel-plan/02-defect-alert-console/plan.md
Defect Alert Console | Alert UI Development | Develop alert list view with filters | Frontend | High | Done | 2026-06-20 | excel-plan/02-defect-alert-console/plan.md
Defect Alert Console | Severity Classification | Configure Critical/Major/Minor logic | AI Team | High | Done | 2026-06-20 | excel-plan/02-defect-alert-console/plan.md
Defect Alert Console | Notification Engine | SMS/Email/Popup alerts integration | Backend | Medium | Done | 2026-06-20 | excel-plan/02-defect-alert-console/plan.md
Defect Alert Console | Testing | Validate alert generation and acknowledgment | QA | High | Done | 2026-06-20 | excel-plan/02-defect-alert-console/plan.md
Virtual Train Inspection Portal | 3D Coach Layout Design | Create coach visualization structure | UI/UX | High | Done | 2026-06-20 | excel-plan/03-virtual-inspection-portal/plan.md
Virtual Train Inspection Portal | Camera Mapping | Map 8 cameras to coach positions | AI Team | High | Done | 2026-06-20 | excel-plan/03-virtual-inspection-portal/plan.md
Virtual Train Inspection Portal | Annotation Overlay | Display AI defect markings | Frontend | High | Done | 2026-06-20 | excel-plan/03-virtual-inspection-portal/plan.md
Virtual Train Inspection Portal | Image Retrieval API | Fetch captured images per coach | Backend | High | Done | 2026-06-20 | excel-plan/03-virtual-inspection-portal/plan.md
Virtual Train Inspection Portal | User Acceptance Testing | Validate inspection workflow | QA | High | Done | 2026-06-20 | excel-plan/03-virtual-inspection-portal/plan.md
Coach Search | Search Criteria Definition | Coach Number / Train Number search | BA | Medium | Done | 2026-06-20 | excel-plan/04-coach-search/plan.md
Coach Search | Search API Development | Historical inspection lookup | Backend | Medium | Done | 2026-06-20 | excel-plan/04-coach-search/plan.md
Coach Search | Search UI | Search and result screens | Frontend | Medium | Done | 2026-06-20 | excel-plan/04-coach-search/plan.md
Coach Search | Validation Testing | Verify retrieval accuracy | QA | Medium | Done | 2026-06-20 | excel-plan/04-coach-search/plan.md
OCR Results Log | OCR Data Schema Design | Define OCR storage structure | Backend | High | Done | 2026-06-20 | excel-plan/05-ocr-results-log/plan.md
OCR Results Log | OCR Results Dashboard | Display OCR records and confidence scores | Frontend | High | Done | 2026-06-20 | excel-plan/05-ocr-results-log/plan.md
OCR Results Log | Image Preview Integration | Raw image viewing feature | Frontend | Medium | Done | 2026-06-20 | excel-plan/05-ocr-results-log/plan.md
OCR Results Log | Accuracy Verification | OCR quality testing | QA | High | Done | 2026-06-20 | excel-plan/05-ocr-results-log/plan.md
Defect Analytics | KPI Definition | Define trends and performance metrics | Business Team | High | Done | 2026-06-21 | excel-plan/06-defect-analytics/plan.md
Defect Analytics | Analytics Data Model | Create reporting datasets | Backend | High | Done | 2026-06-21 | excel-plan/06-defect-analytics/plan.md
Defect Analytics | Charts Development | Trend, category, severity charts | Frontend | High | Done | 2026-06-21 | excel-plan/06-defect-analytics/plan.md
Defect Analytics | Export Feature | Excel/CSV/JSON export | Backend | Medium | Done | 2026-06-21 | excel-plan/06-defect-analytics/plan.md
Defect Analytics | Analytics Validation | Verify calculations | QA | High | Done | 2026-06-21 | excel-plan/06-defect-analytics/plan.md
Camera Health Monitor | Camera Monitoring Logic | Define uptime and health parameters | System Team | High | Done | 2026-06-21 | excel-plan/07-camera-health-monitor/plan.md
Camera Health Monitor | Dashboard Development | Live camera health screen | Frontend | High | Done | 2026-06-21 | excel-plan/07-camera-health-monitor/plan.md
Camera Health Monitor | Alert Integration | Camera failure notifications | Backend | High | Done | 2026-06-21 | excel-plan/07-camera-health-monitor/plan.md
Camera Health Monitor | Health Testing | Simulate camera failures | QA | High | Done | 2026-06-21 | excel-plan/07-camera-health-monitor/plan.md
System Health Dashboard | Infrastructure Metrics Collection | CPU, GPU, RAM monitoring | DevOps | High | Done | 2026-06-21 | excel-plan/08-system-health-dashboard/plan.md
System Health Dashboard | SSD Monitoring | Disk health integration | DevOps | Medium | Done | 2026-06-21 | excel-plan/08-system-health-dashboard/plan.md
System Health Dashboard | UPS Monitoring | Power status monitoring | DevOps | Medium | Done | 2026-06-21 | excel-plan/08-system-health-dashboard/plan.md
System Health Dashboard | Dashboard UI | Health indicators and charts | Frontend | High | Done | 2026-06-21 | excel-plan/08-system-health-dashboard/plan.md
Historical Reports | Report Templates | Daily, Weekly, Monthly formats | Business Team | Medium | Done | 2026-06-21 | excel-plan/09-historical-reports/plan.md
Historical Reports | PDF Generator | Automated report generation | Backend | High | Done | 2026-06-21 | excel-plan/09-historical-reports/plan.md
Historical Reports | Scheduler Service | Automatic report generation | Backend | High | Done | 2026-06-21 | excel-plan/09-historical-reports/plan.md
Historical Reports | Report Validation | Verify report accuracy | QA | Medium | Done | 2026-06-21 | excel-plan/09-historical-reports/plan.md
User Management | Role Matrix Definition | Admin, RDSO, ZR Officer, Staff | Security Team | High | Planned | 2026-06-21 | excel-plan/10-user-management/plan.md
User Management | Authentication Setup | Login, Password Policies | Backend | High | Planned | 2026-06-21 | excel-plan/10-user-management/plan.md
User Management | RBAC Implementation | Role-based access control | Backend | High | Planned | 2026-06-21 | excel-plan/10-user-management/plan.md
User Management | Two-Factor Authentication | OTP/Auth App integration | Security Team | High | Planned | 2026-06-21 | excel-plan/10-user-management/plan.md
User Management | Security Testing | Access control validation | QA | High | Planned | 2026-06-21 | excel-plan/10-user-management/plan.md
AI Inference Management | Model Registry | Maintain deployed YOLO/OCR model versions | AI Team | High | Planned | 2026-06-22 | excel-plan/11-ai-inference-management/plan.md
AI Inference Management | Inference Monitoring | Monitor FPS, latency, GPU utilization | AI Team | High | Planned | 2026-06-22 | excel-plan/11-ai-inference-management/plan.md
AI Inference Management | Accuracy Benchmarking | Compare model performance over time | QA/AI Team | High | Planned | 2026-06-22 | excel-plan/11-ai-inference-management/plan.md
AI Inference Management | Validation Testing | Validate predictions after deployment | QA | High | Planned | 2026-06-22 | excel-plan/11-ai-inference-management/plan.md
Defect Verification Console | Review Workflow Definition | Define human verification process | BA | High | Planned | 2026-06-22 | excel-plan/12-defect-verification-console/plan.md
Defect Verification Console | Verification UI | Approve/Reject detected defects | Frontend | High | Planned | 2026-06-22 | excel-plan/12-defect-verification-console/plan.md
Defect Verification Console | Feedback Capture | Store operator corrections | Backend | High | Planned | 2026-06-22 | excel-plan/12-defect-verification-console/plan.md
Defect Verification Console | AI Retraining Dataset Builder | Generate labeled datasets | AI Team | High | Planned | 2026-06-22 | excel-plan/12-defect-verification-console/plan.md
Defect Verification Console | UAT Testing | Validate review workflow | QA | Medium | Planned | 2026-06-22 | excel-plan/12-defect-verification-console/plan.md
Train Movement Timeline | Timeline Design | Define train passage visualization | UI/UX | High | Planned | 2026-06-23 | excel-plan/13-train-movement-timeline/plan.md
Train Movement Timeline | Event Collection Service | Capture detection timestamps | Backend | High | Planned | 2026-06-23 | excel-plan/13-train-movement-timeline/plan.md
Train Movement Timeline | Timeline UI | Visual inspection timeline | Frontend | High | Planned | 2026-06-23 | excel-plan/13-train-movement-timeline/plan.md
Train Movement Timeline | Playback Feature | Replay train inspection events | Frontend | Medium | Planned | 2026-06-23 | excel-plan/13-train-movement-timeline/plan.md
Train Movement Timeline | Testing | Validate event sequencing | QA | Medium | Planned | 2026-06-23 | excel-plan/13-train-movement-timeline/plan.md
Image Archive Management | Storage Architecture | Define image retention policy | Backend | High | Planned | 2026-06-23 | excel-plan/14-image-archive-management/plan.md
Image Archive Management | Archive Service | Long-term image storage | Backend | High | Planned | 2026-06-23 | excel-plan/14-image-archive-management/plan.md
Image Archive Management | Retrieval Optimization | Fast image lookup | Backend | High | Planned | 2026-06-23 | excel-plan/14-image-archive-management/plan.md
Image Archive Management | Storage Monitoring | Monitor archive usage | DevOps | Medium | Planned | 2026-06-23 | excel-plan/14-image-archive-management/plan.md
Image Archive Management | Testing | Validate retrieval performance | QA | Medium | Planned | 2026-06-23 | excel-plan/14-image-archive-management/plan.md
Train Passage History | Data Model Design | Store train inspection history | Backend | High | Planned | 2026-06-24 | excel-plan/15-train-passage-history/plan.md
Train Passage History | Historical Dashboard | View previous train runs | Frontend | High | Planned | 2026-06-24 | excel-plan/15-train-passage-history/plan.md
Train Passage History | Filtering & Search | Search by date/train/rake | Frontend | Medium | Planned | 2026-06-24 | excel-plan/15-train-passage-history/plan.md
Train Passage History | Validation Testing | Verify history accuracy | QA | Medium | Planned | 2026-06-24 | excel-plan/15-train-passage-history/plan.md
AI Performance Analytics | KPI Definition | Precision, Recall, F1 metrics | AI Team | High | Planned | 2026-06-24 | excel-plan/16-ai-performance-analytics/plan.md
AI Performance Analytics | Analytics Engine | Calculate model metrics | Backend | High | Planned | 2026-06-24 | excel-plan/16-ai-performance-analytics/plan.md
AI Performance Analytics | Dashboard Development | AI performance reports | Frontend | High | Planned | 2026-06-24 | excel-plan/16-ai-performance-analytics/plan.md
AI Performance Analytics | Validation Testing | Verify metric calculations | QA | Medium | Planned | 2026-06-24 | excel-plan/16-ai-performance-analytics/plan.md
Operations Command Center | Operations Workflow | Define monitoring procedures | Business Team | High | Planned | 2026-06-25 | excel-plan/17-operations-command-center/plan.md
Operations Command Center | Unified Dashboard | Single-screen operations view | Frontend | High | Planned | 2026-06-25 | excel-plan/17-operations-command-center/plan.md
Operations Command Center | Incident Tracking | Track system issues and actions | Backend | High | Planned | 2026-06-25 | excel-plan/17-operations-command-center/plan.md
Operations Command Center | Testing | Validate workflows | QA | Medium | Planned | 2026-06-25 | excel-plan/17-operations-command-center/plan.md
Data Synchronization Hub | Message Queue Integration | Kafka/RabbitMQ integration | Backend | High | Planned | 2026-06-25 | excel-plan/18-data-synchronization-hub/plan.md
Data Synchronization Hub | Retry Mechanism | Handle failed transmissions | Backend | High | Planned | 2026-06-25 | excel-plan/18-data-synchronization-hub/plan.md
Data Synchronization Hub | Monitoring | Data flow health dashboard | DevOps | High | Planned | 2026-06-25 | excel-plan/18-data-synchronization-hub/plan.md
Data Synchronization Hub | Testing | Validate reliability | QA | High | Planned | 2026-06-25 | excel-plan/18-data-synchronization-hub/plan.md
Audit & Compliance | Activity Tracking | Log user and system actions | Backend | High | Planned | 2026-06-26 | excel-plan/19-audit-compliance/plan.md
Audit & Compliance | Audit Dashboard | Search and review logs | Frontend | Medium | Planned | 2026-06-26 | excel-plan/19-audit-compliance/plan.md
Audit & Compliance | Compliance Validation | Verify audit coverage | QA | High | Planned | 2026-06-26 | excel-plan/19-audit-compliance/plan.md
Railway Asset Management | Maintenance Tracking | Asset maintenance schedule | Backend | Medium | Planned | 2026-06-26 | excel-plan/20-railway-asset-management/plan.md
Railway Asset Management | Asset Dashboard | Asset lifecycle monitoring | Frontend | Medium | Planned | 2026-06-26 | excel-plan/20-railway-asset-management/plan.md
Railway Asset Management | Validation Testing | Verify asset records | QA | Medium | Planned | 2026-06-26 | excel-plan/20-railway-asset-management/plan.md
Station Monitoring Dashboard | Station Configuration | Configure inspection sites | Backend | Medium | Planned | 2026-06-27 | excel-plan/21-station-monitoring-dashboard/plan.md
Station Monitoring Dashboard | Multi-Station View | Monitor all MVIS locations | Frontend | High | Planned | 2026-06-27 | excel-plan/21-station-monitoring-dashboard/plan.md
Station Monitoring Dashboard | Health Aggregation | Consolidated station status | Backend | High | Planned | 2026-06-27 | excel-plan/21-station-monitoring-dashboard/plan.md
Station Monitoring Dashboard | Testing | Validate monitoring accuracy | QA | Medium | Planned | 2026-06-27 | excel-plan/21-station-monitoring-dashboard/plan.md
Dataset Management Portal | Dataset Registry | Manage training datasets | AI Team | High | Planned | 2026-06-27 | excel-plan/22-dataset-management-portal/plan.md
Dataset Management Portal | Dataset Upload | Upload new labeled data | Backend | High | Planned | 2026-06-27 | excel-plan/22-dataset-management-portal/plan.md
Dataset Management Portal | Dataset Versioning | Track dataset revisions | Backend | High | Planned | 2026-06-27 | excel-plan/22-dataset-management-portal/plan.md
Dataset Management Portal | Validation Testing | Verify dataset integrity | QA | Medium | Planned | 2026-06-27 | excel-plan/22-dataset-management-portal/plan.md
oot Cause Analysis Dashboard | Defect Correlation Engine | Correlate defects with cameras, coaches, train type, speed, and environmental conditions | Backend | High | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | Cause Identification Logic | Identify probable causes using historical data and AI insights | AI Team | High | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | RCA Dashboard Development | Visualize root causes, trends, and contributing factors | Frontend | High | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | Defect Dependency Mapping | Show relationships between recurring defects and assets | Backend | High | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | Failure Trend Analytics | Analyze recurring failure patterns over time | Backend | High | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | Corrective Action Tracking | Track resolution actions and effectiveness | Backend | Medium | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | RCA Report Generation | Generate investigation and audit reports | Backend | Medium | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | Validation Testing | Verify RCA calculations and recommendations | QA | High | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
Root Cause Analysis Dashboard | User Acceptance Testing | Validate operational usefulness with inspectors | QA | Medium | Planned | 2026-06-28 | excel-plan/23-root-cause-analysis/plan.md
AI Model Training Workbench | Training Workflow Definition | Define end-to-end model training lifecycle | AI Team | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Dataset Management | Upload, organize, and version training datasets | AI Team | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Data Annotation Integration | Connect labeling and annotation tools | AI Team | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Training Pipeline Development | Automate YOLO/OCR model training process | AI Team | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Hyperparameter Configuration | Configure epochs, batch size, learning rate, etc. | AI Team | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | GPU Resource Management | Allocate and monitor GPU resources | DevOps | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Experiment Tracking | Track training runs and performance metrics | AI Team | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Model Evaluation Dashboard | Display Precision, Recall, mAP, F1 Score | Frontend | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Model Comparison Engine | Compare multiple model versions | AI Team | Medium | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Model Registry Integration | Store approved production models | Backend | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Automated Deployment Pipeline | Push validated models to production | DevOps | High | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md
AI Model Training Workbench | Training Logs Viewer | View training progress and logs | Frontend | Medium | Planned | 2026-06-29 | excel-plan/24-ai-training-workbench/plan.md

## Event Planning
Task | Status | Owner | Stage | Due date | Notes
| Not started |  | Pre-event
| In progress |  | Day of
| Blocked |  | Post-event
Completed